## Capital Projects
Project ID | Project Name | Sponsor BU | Phase | Budget (RM M) | Spend YTD (RM M) | % Complete | Schedule Variance (days) | RAG | Risk Summary | Target Completion
CP-001 | Solar Farm — Kuala Selangor 50MW | Renewables | Construction | 185 | 142 | 82 | -12 | Amber | Cabling supply delay from China | Q4 2026
CP-002 | TBE-1 Boiler Tube Replacement | Ops-Thermal | Procurement | 18.4 | 1.2 | 15 | 0 | Green | Vendor selection pending Tender Cmte | Q2 2027
CP-003 | Battery Storage Pilot — 20MWh | Innovation | Design | 42 | 8.5 | 28 | 5 | Green | On track | Q1 2027
CP-004 | SCADA Upgrade — Multi-Plant | Ops-Thermal | Execution | 24 | 18 | 76 | 8 | Amber | Cyber assessment additional scope | Q3 2026
CP-005 | Tanjung Biru Jetty Refurb | Ops-Thermal | Construction | 12.5 | 11.8 | 94 | 0 | Green | Final commissioning | Q2 2026
CP-006 | Rooftop Solar — Industrial Estate | Renewables | Tender | 55 | 2 | 8 | -22 | Red | Permit delays from local authority | Q1 2027
CP-007 | HR Workday Migration | Corporate Services | Execution | 8.5 | 5.2 | 62 | 0 | Green | On track, UAT in June | Q4 2026
CP-008 | Plant Digital Twin — PDP-1 | Innovation | Pilot | 6.8 | 2.1 | 32 | 3 | Green | Vendor onboarded | Q1 2027
CP-009 | Coal Stockyard Dust Suppression | Ops-Thermal | Design | 4.2 | 0.8 | 18 | 0 | Green | Concept design approved | Q4 2026
CP-010 | Group ERP Phase 2 | Corporate Services | Execution | 32 | 28.5 | 85 | 18 | Amber | Integration testing slippage | Q3 2026
CP-011 | Wind Resource Assessment — Sabah | Renewables | Study | 2 | 1.4 | 70 | 0 | Green | Met mast data collection | Q3 2026
CP-012 | Cybersecurity Uplift OT/IT | Corporate Services | Execution | 15 | 6.8 | 42 | -8 | Amber | Resource constraint on SOC build | Q4 2026

## Milestones
Project ID | Milestone | Planned Date | Forecast Date | Status
CP-001 | Inverter delivery | 2026-05-30 | 2026-06-12 | At Risk
CP-001 | Mechanical completion | 2026-09-15 | 2026-09-30 | At Risk
CP-002 | Tender Committee approval | 2026-05-26 | 2026-05-26 | On Track
CP-004 | SCADA migration cutover | 2026-08-20 | 2026-08-28 | At Risk
CP-006 | Permit issuance (local authority) | 2026-04-30 | 2026-06-15 | Delayed
CP-007 | UAT sign-off | 2026-06-15 | 2026-06-15 | On Track
CP-010 | Phase 2 go-live | 2026-08-01 | 2026-08-19 | At Risk